## Pt1
Date | Location | Agenda | Items | Questions | Comments | Action | Attendance
2026-03-12 | Melb Conn L2 | First meeting with project supervisor | -Introduction -Project Overview -Outcomes -Timeline -Communication -Fortnightly Meetings -Next steps | -What are the different methods we can use to achieve a better understanding of the domain? Any channels suggested from supervisor? | -Communication: Create teams group with supervisor. -Roles: +Team Leader: Main point of contact, overlook project. (YingJie) +Industry Partner Contact: Replying to enquiries (Vanndy) +Project Manager: Github repository management (make sure it is up to date) (Sylvia and Jerry) +Literature Reviewer (Lead Research): Check research and combine papers others read and have it in GitHub (Yun Gu) -Industry Calls +Ask questions to industry (can try more methods?) +Define client expectations +Weekly calls (in person or online? Clarify) -Computing: +Spartan +Research Server -Submissions: +1 - 2 page progress report. -Milestones 1. Gather literature 2. Establish research question 3. Do analysis of the available data 4. Think of baseline (Submit a report 1-2 pages) Deadline week 4 & 8 The detail report mentions the literature and stuff. The progress report mentions challenges 5. Investigate and study design of the solution 6. Developing the sys 7. Detailed analysis 8. A final report of 2nd semester work -Datasets +Find publically similar datasets to do wavelet analysis (University have?) ***Understanding of project: Based on the clotting nature, we can tell disease. -The company wants to investigate incorporate the time aspect along with frequency can improve the outcomes. -They are using a gel to do experiments to mimic the properties of blood ***Meetings will be 2pm-3pm (In person or online) | 1. To add our supervisor to Teams Channel 2. Create a meeting minute 3. Create Github repo and make sure it's private 4. Organize literature review 5. Find public datasets 6. Meeting minutes 7. Everyone to read more about Fourier analysis vs Wavelet analysis | Everyone
2026-03-19 | Melb Conn L2 & Online | Meeting before Industry Host meeting |  |  | -Just based on Analysis, which is the best respresentative gel system. (For blood clotting) -We need to understand what data they have first 1. Start by checking literature reviews 2. How to categorize those LR 3. Check other domains how they are working with wavelets to get the current state of the art (eg. Wavelet neural networks) ***Can ask clients their current methods and research into Wavelets -Check data science-wise, what is the current trend towards wavelets? -Use google scholars, Use + sign (eg. Fourier + Wavelets). After understand theory, filter for most recent. +Client meeting process (Agenda): 1. Introduce 2. Project scope (These are the objectives, please give more detail and clarify "....") 3. Ask client what are the project deliverables? Dashboard? Report sufficient? What are the performance metrics? 4. What is the timeline for objectives? 5. Last 10mn about the timeline of data access and plan for next meetings. | 1. Read and understand Fourier and Wavelets 2. Check wavelets applied in other domains 3. Create a basic python script for wavelet to do a small analysis to understand. 4. Each of us to do a brief explanation of Wavelets and Fourier 5. Create questions for the client | Everyone
2026-03-24 | Teams | Meeting with Industry Host | Item: Introductions Allocated time: 10 minutes Notes: The team will formally introduce and get acquainted with the industry host. Item: Project Scope/Overview Allocated time: 20 minutes Notes: To clarify expectations of what the overall project will cover and what the student team will be responsible for. Item: Expected Deliverables/Outcomes Allocated time: 20 minutes Notes: Performance metrics, key indicators success/failures. Item: Timelines Allocated time: 5 minutes Notes: Expected frequency of updates/results delivery for certain stages of the project. Item: Communications and Next Steps Allocated time: 5 minutes Notes: How communication between the team and host will look like moving forward. | We’ve gone through the project brief and prepared a few questions to better align our understanding and expectations. 1.Given that our team does not have a strong physics background, we would appreciate some guidance on how performance is typically evaluated in this context. How do we determine which gel system performs better? Answer: The gel system can just be any fluid that has properties representative of blood or blood clot formation. Are there specific metrics or indicators we should focus on? 2.Could you clarify whether the project will primarily rely on existing datasets, or if there is an expectation to source additional data or conduct further experiments? Answer: The datasets are to be acquired through open-source means. 3.We’d like to better understand the current baseline approaches. How have Fourier Transform or STFT-based methods been applied so far? Are there any references, prior studies, or internal examples we could review? For the wavelet approach, do you already have a prototype or direction in mind, or would you prefer us to explore and develop this more independently? Answer: We are recommended to do Literature Review and develop independently. 4.For the wavelet-based analysis: Is there a preferred framework or specific methods you would like us to focus on (e.g., CWT vs DWT, specific wavelet families)? Are there any preferred coding environments or tools (e.g., Python, MATLAB, R)? Answer: It is up to the team to decide. 5.From your perspective, what would define a successful outcome for this project? Are there particular performance benchmarks or goals we should aim for? For example, improved temporal resolution, clearer detection of transition points, or better interpretability of results? Answer: The expected outcome is to have a model that is able to do real time signal data transformation using time based frequency analysis. The technique and model does not have to be better, it is simply to explore the feasibility of this solution and if the technique outperforms the current model, it is icing on the cake. 6.Could you also clarify the expected form of deliverables? For instance, a research report, a prototype analysis pipeline, or something closer to a production-ready solution? Answer: It is more of a prototype, but should have proper pipeline and documentation for the team at Haemograph to further develop into production. As long as it helps in reaching our conclusion of the technique. 7. Are there any particular challenges or risks that you anticipate in this project that we should be aware of early on? | 1. Datasets get it ourselves from the link? From explanation, we can determine any gel system. Any recommended? Answer: Use with synthetic blood, hence recommended to find dataset that relates to that (open-source). ***Key: Dynamic system, property always changing (eg. with medication, diff from without medication) | 1. Put together documentation of the articles shared. Go through articles and go into detail. (Literature review Rheuology, and other articles, different data processing systems for real time, different domains for this problem.) and possibly look into representative fluid datasets. 2. Look up how blood clot is formed. (Understand a blood) 3. Have a problem statement draft and what it looks like (aims and objectives of this project) | Everyone
2026-03-26 | Online + In Person | 3rd Supervisor Meeting | Talk about industry meeting |  | 1. Ensure that Literature has similar dataset. 2. For initial state, it doesn't have to be similar to blood yet. 3. At this state, Haemograph wants to identify the features that are availabe to do frequency based analysis and then add real-time. Model is only feasible if we find that there is a property that we identified the features that can be analysed over time. 4. Go through papers to find the gap of the current method, why is time not being used yet? Make sure when reading papers to check the techniques and what they are trying to achieve. | 1. Find dataset and clarify with host in next meeting. Do preliminary analysis on it and make sure to understand the data. 2. Read papers and find the research gap (What methods are being used in current work for blood) 3. What is the exact metric we are going to measure it?
2026-04-02 | In Person | 4th Supervisor Meeting | Talk about papers we read |  | -There is a paper shared by Yun Gu about having a criterion for when a gel point happens. (Fourier) -Read some wavelets paper and look at the functions they used. | To do: 1. Come up with problem statement for Ragil -Should have objectives -Share dataset and link. 2. Open Source Dataset 3. List of papers and if he wants us to go through. 4. Any questions or problems check with ragil at the end of meeting (metrics to identify how good or bad) 5. Look at Frequency Gating (similar to Fourier) it considers different segments. 6. Replicate analysis on Fourier and try to apply on Wavelet in Python. ***We have a problem statement from client, we can try to come up with our own as well | Yun Gu, Sylvia, Yingjie, Vanndy, Saumya
2026-04-16 | In Person + Online | Supervisor Meeting | Talk about Problem Statement |  | -Add the References -Link Evaluation Criteria to Research question -Combine smart objectives with deliverables. -Find dataset with state change in the material -What is the gap? Rheology or Bio-wise. Should create a mind map for the gap. | For Ragil: 1. Plot some graphs based on the datasets 2. Problem Statement Draft 3. Implement the transform | Everyone
2026-04-22 | Online | Group Meeting | Finalise problem statement |  | We have updated Yun Gu draft of the problem statement and finalised the first draft. This will be presented to Haemograph for feedback. We also sent the statement to our supervisor prior to sending directly to host. | 1. Send problem statement to supervisor 2. Send problem statement to host
2026-04-23 | In Person + Meeting | 5th Supervisor Meeting |  |  | -We can try using Mendely for the literature. -Try to find the best method (What are the evaluation criterias?) Select dataset, select algos, do final analysis with the algos. -Problem statement needs updating Eval Criteria: 1. Go into specifics (not just high level) 2. Explanation of the literature review (Exploratory analysis... .) Ex: Mind maps and show gaps 3. Which model, analysis steps, total timeline (Eg. Initial algos, what will go in secondary analysis.. .) 4. Presentation Clear (Should know what we are talking about) Everyone should engage. | 1. Structure the literature review 2. Start working on the report 3. Update problem statement 4. Try different algos with the datasets and compare them with each other | Everyone
2026-04-23 | Online Meeting | 2nd Industry Meeting | Problem Statement and Dataset review | 1. Are we going in the right direction? 2. Anything in the problem statement that needs refining? 3. Should we get more of the same type of datasets? 4. Are there specific measurement tools that should be leaned towards? Or it doesn't matter? | 1ST Characterise 1. What is the sampling rate of dataset? Does it help identify the techniques (***Sampling Rate) 2. Keep in mind: Be able to define what is resolution of the system? When making use of datasets, come up with objective missions. Eg. Define essential criterion. Maybe not a single criterion, but multiple criterion. Is there a technique that can be used for real-time analysis of rheology, providing outcome that is not visible in current techniques? 3. Identify distinct artifcats in data, if may not be uncovered using frequency vs in time? 4. Provide real time outcomes while identifying these artifacts and providing better resolutions. Especially for non-stationary signals. ***We can have just 3 obj 5. Good way to have better signal to noise ratio 6. Quantify how we kept these parameters mentioned. What are measures to quantify the system better. Eg. Making use of measurements that helps quantify (something that can be used to quantify in engineering terms) Eg. Sensitivity of the system, the responsiveness, signal to noise ratio. 7. Make sure the method is able to process data in real time, or identify artifacts (what is the dynamic response of the system). Eg. Shear, Stress. Eg. As stress increases, for inputs or outputs as such, does the method help us get better information vs a Fourier Transform. Can we identify any non-stationary char of the system. Then we can look at how responsive it is when the values move up or down. 8. We can look at drift, phase shift in applying these algos. Need to be able to quantify information as much as possible and think about accuracy, applicability, the error band (could be from noise, data having drift, and other offsets. If we have an error band, how does ours work vs other methods) 2ND Part 1. What is requirement of stakeholder (The technique we will apply) 2. Stakeholder analysis needs to be performed (Have questionnaire about the rheometer) -Size of data -Sampling rate -Type of rheometer 3. Minimum set of requirements needs to adhere to so the methodolgy solves stakeholder problem. 4. What can we identify in the system? Noise... etc etc? So we can do real-time processing. 5. Identify the pros and cons of the different transforms | 1. Stakeholder analysis 2. Understanding of system => Technique Analysis 3. Requirement analysis for our Framework 4. Go back to literature and identify different issues of the different techniques out there (We should have a presentation of the techniques we identified). We need to show techniques we looked at and the pros and cons. | Everyone
2026-04-30 | In Person | Supervisor Meeting | Stakeholder analysis |  | How to choose algo: -Work with noisy data -Non-stationary data -Different sampling rates | 1. Finalise the problem statement 2. Stakeholder analysis to check with Ragil what he thinks (And requirement analysis) 3. What is the signal to noise ratio, check with Ragil? 4. Check if we can create synthetic datasets? (What functions are suggested, if any?) | Yun Gu, Sylvia, Fengjie, Vanndy, Saumya
2026-04-30 | Online | Item: Problem Statement Review Allocated time: 20 minutes Notes: Item: Requirement Analysis Review Allocated time: 20 minutes Notes: Item: Questionnaire Allocated time: 15 minutes Notes: To clarify expectations of what the overall project will cover and what the student team will be responsible for. Item: Next Steps Allocated time: 5 minutes Notes: | Problem Statement Requirement Analysis Questionnaire (Later) |  | 2. Requirement Selection: -Check number 2 comment -Check number 3 if we can derive time from other params -Check 4, it is quite vague | 1. Before next meeting, do weighting on our essential criterian and tradeoff criterians. (Quantitative version of our techniques. -Once identified, we can look back for any algorithms we define as feasible or not based on that. 2. Update problem statement based on suggestion 3. Presentation | Everyone
2026-05-07 | In Person | Supervisor meeting
2026-05-07 | Online | Industry Meeting |  | 1. What is sufficient as Preliminary Analysis? 2. Can we still use Gel-Point or should we just study the overall changes? | Requirement Analysis -We need to have actual quantitative comparison so it is more factual. -We only need to test the essential criterion -What is the scoring Low,Med,High mean +Trade-off Requirements -#3 How to come up with quantitative for our tradeoffs? Give score for each trade-off (Need parameter of choice) -#4 signal to noise ratio might be good parameter, how about resolution? -#6 level we can identify. We can rely on literature to come up with parameter (can be sensitivity... .) -#7 how to capture that information (harmonics can be identified at all of them). How are we going to measure it (parameter can be identifiying n harmonic frequency by accuracy... .) For example total distortion measure and get values to compare. -Definition of rating should be specific to essential criteria. ***Making the setup more quantitative. -Is there a lot of Phase difference in them? 1. Preliminary Analysis? -Number referring to check if the data is meeting the requirements -We will stick with literature data -Feasibility study completed if quantitative value works 2. Gel-Point? -When shear fluid continues to evolve. Gel-Point is just one property, so we want to look at all the properties. Viscosity, elasticity, and more transition point. -We can just focus on Gel-Point | 1. Should be quantitative for Requirement Analysis 2. Send powerpoint by Monday
2026-05-21 |  | Supervisor meeting |  |  | Report: -Mathematical rigour needs to be provided -Can include from studies -Write long form in first occurrence for every short form. -Separate table for what work we are going to assign.

## Pt2
Date | Location | Agenda | Items | Questions | Comments | Action | Attendance
2026-07-30 |  | Supervisor Meeting |  |  | Required by Uni 1. Show Cooperation 2. Need logs for the coding 3. Marking strictly ruberic 4. Peer review ------------------------------------ Next Industry Meeting: 1. Share what we have done 2. Check with specific format Ragil wants for the code to be delivered. ------------------------------------- For Part2 of the project 1. Identify the pros and cons of the methods | 1. Update for meeting with Ragil 2. Test the different methods | Everyone
2026-07-31 |  | Industry Meeting | 1. Datasets 2. Recap of what we have done |  | -Ragil Identified datasets -Articles regarding the datasets -We can reach out to authors to share resource & code -If next week we can't identify the datasets, we should try to email the researchers ----------------------------------------- What does Ragil expect? 1. Build a consistent data pipeline for LAOS and step-up/down measurements. 2. Validate conventional LAOS and transient rheology metrics. 3. Develop CWT/DWT/signal transformation features that measure time-dependent nonlinearity and/ or structural relaxation. 4. Test whether wavelet features distinguish- strain amplitude; step magnitude; step direction; stable versus transient portions of a measurement. 5. Identify a minimal feature set that could later be calculated from the Haemograph rheometer. ----------------------------------------- Use the verification pipeline Dr Ragil gave, and find out if the method can be used on Rheometer. ----------------------------------------- Checklist for methods: -Specifications? -Dataset non-stationary? -Test it on rheometer 1. Preparation work (Identify what ground truth looks like) 2. Implement algo to compare based on our specifications 3. Use algo on their rheometer ---------------------------------------- Deliverables: 1. Report (Referencing to github) 2. Github | 1. Dr Ragil to share the datasets and articles 2. Each of us spend 10mn of the papers we looked into - background study, research obj, concept of method, results they got and how it compares with existing methods. Last 10mn choose 3 papers. 3. We need to try to identify what the model is for articles: https://scholar.google.com/scholar?oi=bibs&hl=en&cites=2149823699155869639&as_sdt=5 | Everyone
2026-08-04 |  | Ian Meeting |  |  | Anomaly detection? Make it into a classification problem instead? Change point detection? (can frame it as hypothesis detection)
2026-08-06 |  | Supervisor Meeting |  |  | Papers: 2. Yingjie The paper suggests: -Blood has memory -We want to include that into the equation. 1. Fengjie -Incorporate Lamda into the model to model the realoux breakdown of the blood structure. ====================================================================== Ruberic breakdown -How complex is the report? Did we make good progress and tried enough techniques? -Why specific method or techniques with notations. Plots clear? Answering project objectives Tables: Any metrics, and is it relevant +Penalties: -We need meeting minutes and github logs. -Year long project, so not much progress is = mark % adjustment | 1. Start from the initial model (Base) 2. Look at the computer science aspect on how to improve it as well. (Mechanistic => ML) 3. Replicate the code (find online or do on our own?)
2026-08-07 |  | Industry Meeting |  |  | Presenting the papers: -Sylvia went first with the presentation -Fengjie went second introducing the model and Lamda for realoux breakdown -Yingjie went third sharing how it can be implemented | 1. Next meeting to discuss remaining papers. 2. See how we can implement some of this to our methods.
2026-08-13 |  | Supervisor Meeting |  |  | Sylvia tested the models End goal: -Integrate feature engineering in papers with wavelets? Should ask Ragil | 1. Ask Ragil if he wants us to implement or just understand the feature engineering part conceptually 2. Try applying it to wavelets that is presented in the papers 3. This semester, find method to identify clotting -------------------- Each member to have some slides to present what we've done
2026-08-14 |  | Industry Meeting |  |  | What it is about? -What is the impact of Wavelets? | -See how we can implement it into our methods
2026-08-20 |  | Supervisor Meeting |  |  | Fengjie, Yun Gu, Vanndy and Sylvia updated on findings from respective papers | We should try to work on optimizing it to see if it gives better results.
2026-08-24 |  | Industry Meeting |  |  |  | Want to continue working on replicating and testing feasibility of different methods
2026-08-27 |  | Supervisor Meeting |  |  | Should try to continue replication to see issue ***Next week We will discuss what ML we can use for them | -Meet with supervisor and update him
2026-09-01 |  | Industry Meeting |  |  | Want to put Giesekus Model on hold as unable to reproduce *Some suggestions on how to impement ML 1. What is the signal and what is the noise, how to detect transience, are we able to utilize STFT... *Oscillitary flow data from the rheometer | To update him again on Friday this week -We want to choose some algorithms first and confirm together For later: -Add transience to the model
2026-09-04 |  | Industry Meeting |  |  | -Sylvia shared findings via email as busy couldn't attend -Vanndy still working on global temporal parameter optimization -Yingjie started the meeting by sharing findings (Tried to fit manual lambda values to make the model better. It improved by a little bit). -Yun Gu shared: LAOS experiments, showing that FFT can show the harmonics between 3rd, 5th and 7th. STFT can shows a drop in stress amplitude over time with steady strain levels (CWT supports this) Then DWT | We will eventaully work with the combination that works for us. Regardless of transform, there may be overlapping information that each transforms provides. -We should be able to suggest pros and cons of what combination we come up with. (FFT, STFT, CWT, .. .) and literature driven. (Why the differences are there and such.. ?) ***Outcome wanted is frequency band where energy concentration is, and try to relate it back to literature.
2026-09-10 |  | Supervisor Meeting |  |  | -Sylvia fit the signal transformation (FFT, STFT, CWT, DWT...) with donor 5. -Vanndy no new updates yet. Work with Yingjie and Sylvia for t-ESSTV -Fengjie still looking into more of it -Yun Gu shared harmonics findings and did analysis to see the transient part. Conclusion: Both FFT and STFT can find 3rd harmonic, and STFT can see every window. =========================================================== | -Change point detection algorithms -Signal processing -Set a time for internal discussion Possibly combine algorithms (t-ESSTV + change point) with mechanistic model (...+ anamoly ML?) =>See if it gives different results (analysis part)
2026-09-11 |  | Industry Meeting |  |  | -Yun Gu updated her work. +FFT and STFT comparison in terms of capturing harmonics (they are similar) +Tried different windowing amount (from 4 to 2) to see how it affects the third harmonics ratio (Ragil wants to add more noise) -Ragil thinks it's better to continue working on multiple models Question: Change point detection algo? Answer: Need to know how we can utilize the algo to explain the output in physiological terms. For example, A (paper) B(our algo), so how do we make sure technique B is validated? (with literature?) We need to be able to have ground truths of some sort. | -To check how to use the correct window size -Pipeline and check deliverables
2026-09-12 |  | Group Meeting |  |  | We want to work on just the stress predictions and analysis of approach first If we do the ML model as well, we need to have a proper pipeline and proposed model. Fengjie and Vanndy to look into this in spare time. At the moment, focus on replicating t-ESSTV parameters. | -Do parameter tuning (Fengjie, Vanndy) -Do pipeline (Fengjie, Vanndy) -Continue testing t-ESSTV with Fengjie and Vanndy (Sylvia) -Yun Gu to continue looking at her model -Yingjie to help setup a meeting with Michael
2026-09-17 |  | Supervisor Meeting |  |  | We shared our approach with the mechanistic model which we want to run parallelly: 1. Signal processing => to detect changepoint 2. Mathematical algorithm model (t-ESSTV) to model stress and then => detect clotting point with stress Both methods will reconfirm each other's outputs. | -Vanndy to test with Sylvia the parameters that are tuned and see if it is useful -To present to Ragil and Michael if this is an ok approach. -Vanndy to draw a pipeline to show to Ragil
2026-09-18 |  | Industry Meeting |  |  | Dr Ragil interested in knowing the clot *happening in advance* if we use ML -Path A traditional -Path B t-ESSTV (mechanical model) feature selection validation step can be here -Path C have signal transformation Then we get 3 streams (we can combine the transformed and physical features to identify the transformation) He wants to be able to get advanced detection, how quickly the transition occurs, quantitative (detection time, delay time, feature contribute to detection, what is magnitude of feature, what is confidence, basically why is it labelled as transition?) We want to know when something happened, and why? (Any thresholds? Easier for comparing detected vs reference)
2026-10-08 |  | Supervisor Meeting |  |  | Present our work and the presentation The flow is -Introduction 30-45s -Recap of project ... 5. Experimental Data 6. Integrated Discussion: How we combine the results | Expectations: 14/20 for median (most groups get that marks) 20/20 must be exceptional, they will be in the 3mn thesis standard Goals articulated Methods introduced in accessible way (nice story, clear enough, high level enough for audience. No need to go into low level) Strong conclusions or recommendations. Results can be left fo reports, or use examples to explain (make interesting) Clarity of english must be considered. Reading script will lower score. All group members equally present. 15mn long timer for presentation. Penalized if exceed. Accessible to general audience. Look into when certain methods fail. +Need to do statistical comparison Use the RMSE to do freedman test to see if it's significant. (Wavelet better than all others) Wilcox test. Take two pair of algo to see if it's statistical Ctritical differeince diagram. Bar connected no difference. ==================================================================== Test run next Thursday.
2026-10-09 |  | Industry Meeting |  |  | Can we detect noise injected? That would be interesting. | 1. To update the conventional method and check crossover since graph shows only divergence 2. Synthetic properly generated (Just need to clarify the rules?) 3. DWT Slides 1. Need slide to address phase 1 and how it changed over time (add what are deliverables) 2. Gantt chart for phase 1, did we meet objectives for gantt chart for phase 2? Limitations and future study page? (dataset?.. for future studies)
2026-10-15 |  | Supervisor Meeting |  |  |  | 1. Add something to show LAOS what is it 2. The graphs needs to be more clear (Increase visibility) of graphs | -Check if tables are clear? and summarizes -Final conclusion write the suggested future work -Document the usage of GenAI (logs of AI) -Need access to github for Saumuya and store GenAI Do the peer review and stick the deadlines.
2026-10-16 |  | Industry Meeting | Capstone Presentation |  |  | -Note some future directions -Which one would we choose? Combination, and why? 2 meetings next week for proper handover if possible. Will check with others. 1. Github 2. Report